## Sheet1
Date | Priority | Task name | User Story | Estimated Time | Story Points | Status | Team Members
2018-03-27 |  | Sprint 1
| S | Research feasible glucose levels for diabetic patients | 1. As a patient, I want to know how much insulin is needed, so that I can stay healthy. | 30 minutes | 10 | Not started | Clay
| M | Create a UI that allows the patient to input their insulin information. I.e. it should allow them to type in the type of insulin they use and what the feasible glucose level is for them | 1. As a patient, I want to know how much insulin is needed, so that I can stay healthy. | 30 minutes | 10 | Not started | Jack
| M | Create a MySQL table with attributes that accepts and stores a patient's insulin information | 1. As a patient, I want the product to monitor my blood sugar using a sensor so that I can keep track of my glucose levels. | 10 minutes | 7 | Not started | Micah
| S | Allow the user to turn the insulin pump program off whenever they choose. Input an action as part of the UI that allows this. | 5. As a patient, I want the product to stop administering insulin if I remove the pump so that insulin is not wasted, and I am not over-medicated when I reattach the pump. | 5 minutes | 3 | Not started | Katherine