## Sheet1
Task | User Story | Estimated Time | Status | Team Members
Sprint 1
Research feasible glucose levels for diabetic patients | 1. As a patient, I want my insulin pump to accurately maintain my glucose levels, so that I can stay healthy. | 2 hours | Complete | Clay
Create a UI that allows the patient to input their insulin information. I.e. it should allow them to type in the type of insulin they use and what the feasible glucose level is for them | 1. As a patient, I want my insulin pump to accurately maintain my glucose levels, so that I can stay healthy. | 2 hours | Complete | Jack
Create a MySQL table with attributes that accepts and stores a patient's insulin information | 11. As a patient, I want my data to have the option of being uploaded online, so that I can access the information with ease and track it at any time. | 2 hours | Complete | Amanda and Dante
.Allow the user to turn the insulin pump program off whenever they choose. Input an action as part of the UI that allows this. | 5. As a patient, I want the product to stop administering insulin if I remove the pump so that insulin is not wasted, and I am not over-medicated when I reattach the pump. | 1 hour | Complete | Katherine
In the model, there should be variables created that match the variables of the table in the mySQL database. | 3. (Non-functional) As an administrator, I want this project's database to be coded in MySQL, because my team can maintain it easier. | 1 hour | Complete | Amanda and Katherine
In the model, there should be a constructor method (if necessary) and getter and setter methods for each variable that was created in the database. | 3. (Non-functional) As an administrator, I want this project's database to be coded in MySQL, because my team can maintain it easier. | 1 hour | Complete | Katherine and Amanda
Creating the blood sugar GUI for the input history | 2. (Non-functional) As a user, I want this machine to maintain my blood sugar, or else I am in risk of death. | 10 days | Complete | Jack
Creating the blood sugar GUI for the patient history | 2. (Non-functional) As a user, I want this machine to maintain my blood sugar, or else I am in risk of death. | 10 days | Complete | Clay
Sprint 2
Create code in the controller to match the key elements in the patient homepage UI | 1. As an administrator, I want this project to be coded in Java and JavaFX, so my team can maintain it easily. | 2 hours | in progress | Jack
Create code in the controller to have the key elements of the patient homepage UI have an appropriate action | 1. As an administrator, I want this project to be coded in Java and JavaFX, so my team can maintain it easily. | 2 hours | in progress | Jack
Have team members who worked on the patient homepage UI communicate with the team members who made the patient information table of the database so that the elements of the UI will match the description the elements of the database | 3. As an administrator, I want this project's database to be coded in MySQL, because my team can maintain it easier. | 2 hours | in progress | Jack, Clay, Amanda, Katherine
Have team members who worked on the patient history portion of the UI communicate with the team members who made the patient history table of the database so that the elements of the UI will match the description of the elements in the database | 3. As an administrator, I want this project's database to be coded in MySQL, because my team can maintain it easier. | 2 hours | in progress | Jack, Clay, Amanda, Katherine
Create code in the controller to connect the patient homepage UI to the patient information table of the database | 10. As a patient, I want the ones who care about me to be notified via an alert system when I am in trouble, so they may assist me. | 2 hours | Not started
Create code in the controller to connect the patient history portion of the UI with the patient history table of the database | 9. As a patient, I want the product to contact emergency services if I am unable to respond to warning messages, so that my life will be saved. | 1 hour | Not started
Animate the patient's glucose level graph to follow the glucose level of the patient. This should work with the alert system to notify the patient if their glucose level is too low or too high. | 8. As a patient, I want to be notified when my insulin levels in the pump are low, so that I know when to replenish it.
In the GUI, an action should be created to allow the patient to display their glucose levels. (Should be part of the glucose level graph) | 7. As a patient, I want the product to display a message, so that I am aware of what is going on with my glucose levels. | 2 hours | Not started
The insulin pump program should have an alert system to notify the patient when his/her insulin pump is running low on insulin. (Possibly have sounds implemented with this process) | 8. As a patient, I want to be notified when my insulin levels in the pump are low, so that I know when to replenish it. | 3 hours | Not started