## Sheet1
Date | Priority | Task | User Story | Estimated Time | Status | Team Members
2018-03-27 |  | Sprint 1
| S | Research feasible glucose levels for diabetic patients | 1. As a patient, I want my insulin pump to accurately maintain my glucose levels, so that I can stay healthy. | 2 hours | In progress | Clay
| M | Create a UI that allows the patient to input their insulin information. I.e. it should allow them to type in the type of insulin they use and what the feasible glucose level is for them | 1. As a patient, I want my insulin pump to accurately maintain my glucose levels, so that I can stay healthy. | 2 hours | In progress | Jack
| M | Create a MySQL table with attributes that accepts and stores a patient's insulin information | 11. As a patient, I want my data to have the option of being uploaded online, so that I can access the information with ease and track it at any time. | 2 hours | In progress | Micah
| S | Allow the user to turn the insulin pump program off whenever they choose. Input an action as part of the UI that allows this. | 5. As a patient, I want the product to stop administering insulin if I remove the pump so that insulin is not wasted, and I am not over-medicated when I reattach the pump. | 1 hour | In progress | Katherine
2018-03-29 |  | Sprint 2
|  | In the UI, there should be a field for the patient to input the grams of carbohydrates that they are planning to consume for their meal or snack, so the insulin pump program will know how much bolus insulin should be injected. | 3. As a patient, I want to be able to program how much bolus insulin I need, so that the insulin pump will deliver it to cover the carbohydrates in each of my meals or snacks. | 2 hours | Not started
|  | In the database, there should be a location to store the amount of bolus insulin used and the grams of carbohydrates that the insulin covered | 3. As a patient, I want to be able to program how much bolus insulin I need, so that the insulin pump will deliver it to cover the carbohydrates in each of my meals or snacks. + 12. As a doctor, I want to be able to access my patient's insulin pump information, so that I can ensure his/her safety and instruct my patient on better use of the pump. | 1 hour | Not started
|  | In the UI, there should be a place for the patient to make their meal/snack schedule, so the insulin pump will know that it should continuously deliver basal insulin in between meals. | 2. As a patient, I want basal insulin to be continously delievered over 24 hours, so that I don't have to use an insulin injection pen. | 2 hours | Not started
|  | In the database, there should be a location to store the amount of basal insulin used in a 24 hour period. | 2. As a patient, I want basal insulin to be continously delievered over 24 hours, so that I don't have to use an insulin injection pen. + 12. As a doctor, I want to be able to access my patient's insulin pump information, so that I can ensure his/her safety and instruct my patient on better use of the pump. | 1 hour | Not started
2018-04-03 |  | Sprint 3
|  | In the UI, the patient should be able to enter their emergency contact information (i.e. their primary doctor's information and other information of people close to them), so they are contacted. | 10. As a patient, I want the ones who care about me to be notified via an alert system when I am in trouble, so they may assist me. | 2 hours | Not started
|  | In the database, the emergency services phone number should be saved as well as other emergency contact information of the patient. | 9. As a patient, I want the product to contact emergency services if I am unable to respond to warning messages, so that my life will be saved. | 1 hour | Not started
|  | In the UI, there should be a field for the patient to manually input the amount of insulin they want the insulin pump to inject. | 4. As a patient, I want to be able to program the insulin pump to make correctional or supplemental doses when I ask it to, so that I don't have to use an insulin injection pen. + 5. As a patient, I want to be able to control the amount of insulin given to me by the pump before and after I exercise, so that I do not risk hypoglycemia. | 2 hours | Not started
|  | In the database, there should be a place to record how much insulin the patient made the insulin pump inject. | 4. As a patient, I want to be able to program the insulin pump to make correctional or supplemental doses when I ask it to, so that I don't have to use an insulin injection pen. + 5. As a patient, I want to be able to control the amount of insulin given to me by the pump before and after I exercise, so that I do not risk hypoglycemia. + 12. As a doctor, I want to be able to access my patient's insulin pump information, so that I can ensure his/her safety and instruct my patient on better use of the pump. | 1 hour | Not started
2018-04-05 |  | Sprint 4
|  | In the UI, an action should be created to allow the patient to display their glucose levels. | 7. As a patient, I want the product to display a message, so that I am aware of what is going on with my glucose levels. | 2 hours | Not started
|  | The insulin pump program should have an alert system to notify the patient when his/her insulin pump is running low on insulin. | 8. As a patient, I want to be notified when my insulin levels in the pump are low, so that I know when to replenish it. | 3 hours | Not started
|  | In the UI, a field should be created to allow the patient to input the amount of insulin that they injected when the insulin pump was disconnected. | 14.As a patient, I want to be able to tell the pump if I have administered a certain amount of insulin to myself by other means than the pump so that the pump does not give me too much insulin. | 2 hours | Not started
|  | In the database, there should be a place to record how much insulin the patient injected when the insulin pump was disconnected. | 12. As a doctor, I want to be able to access my patient's insulin pump information, so that I can ensure his/her safety and instruct my patient on better use of the pump. | 2 hours | Not started
|  | In the UI, the patient should be able to enter in a PIN to access their insulin pump's interface. | 13. As a patient, I want child-lock options for my insulin pump so that my children are not able to mess with it and harm themselves or myself doing so. | 2 hours | Not started